## Team
Initials | First | Last | Email | GitHub Username
JJ | Justin | John | jjohn5@stevens.edu | jjohn50
AZ | Angelina | Zaccaria | azaccari@stevens.edu | Angelina-Zaccaria
OP | Olivia | Powers | opowers@stevens.edu | olivepowers
JL | Jennifer | Lloyd | jlloyd2@stevens.edu | jlloyd57
MD | Matthieu | Dupuy | mdupuy@stevens.edu | matt3327
|  |  | GitHub Repository: | https://github.com/jjohn50/SSW-555-Project

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US00 | Creating datetime objects | AZ | Done
1 | US01 | Dates before current date | JJ | Done
1 | US02 | Birth before marriage | JJ | Done
1 | US03 | Birth before death | AZ | Done
1 | US04 | Marriage before death | AZ | Done
1 | US05 | Marriage before divorce | OP | Done
1 | US06 | Divorce before death | OP | Done
1 | US07 | Less then 150 years old | JL | Done
1 | US08 | Birth before death of mother | MD | Done
1 | US09 | Birth before marriage of parents | JL | Done
1 | US10 | Marriage after 14 | MD | Done
2 | US11 | No bigamy | JL | Done
2 | US12 | No child born after divorce | JL | Done
2 | US13 | Conception before Fathers Death | JJ | Done
2 | US14 | Parents not too old | JJ | Done
2 | US15 | Siblings spacing | MD | Done
2 | US16 | Multiple births <= 5 | MD | Done
2 | US17 | Fewer than 15 siblings | OP | Done
2 | US18 | Male last names | OP | Done
2 | US19 | No marriages to descendants | AZ | Done
2 | US20 | Siblings should not marry | AZ | Done
3 | US21 | First cousins should not marry | JL | In Progress
3 | US22 | Aunts and uncles | JL | In Progress
3 | US23 | Correct gender for role | MD | In Progress
3 | US24 | Unique IDs | MD | In Progress
3 | US25 | Unique name and birth date | JJ | In Progress
3 | US26 | Unique families by spouses | JJ | In Progress
3 | US27 | Unique first names in families | AZ | In Progress
3 | US28 | Corresponding entries | AZ | In Progress
3 | US29 | Include individual ages | OP | In Progress
3 | US30 | Large age gaps between couples | OP | In Progress
4 | US31 | Order siblings by age | JL | TBD
4 | US32 | List deceased | JL | TBD
4 | US33 | List living married | MD | TBD
4 | US34 | List living single | MD | TBD
4 | US35 | List multiple births | AZ | TBD
4 | US36 | List recent births | JJ | TBD
4 | US37 | List recent deaths | JJ | TBD
4 | US38 | List upcoming birthdays | OP | TBD
4 | US39 | List upcoming anniversaries | OP | TBD
4 | US40 | Reject illegitimate dates | AZ | TBD

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Burndown Chart
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2020-09-20 | 24 |  | 0
Sprint 1 | 2020-09-27 | 33 | -9 | 250 | 120 | 125
Sprint 2 | 2020-10-05 | 12 | 21 | 480 | 135 | 102.2222
Sprint 3 | 2020-10-19 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2020-11-02 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Hrs | Code Velocity
Start | 2020-09-20 | 40 | 10 | 0 | 0 | 0
Sprint 1 | 2020-09-27 | 30 | 10 | 720 | 7.4167 | 97.0787
Sprint 2 | 2020-10-12 | 20 | 10 | 685 | 8 | 4.375
Sprint 3 | 2020-11-02 | 10 | 10 | 0 | 0 | 0
Sprint 4 | 2020-11-16 | 0 | 10 | 0 | 0 | 0
Total time Frame: |  | 43 days
6 weeks and 1 day

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US00 | Creating datetime objects | AZ | Done | 60 | 60 | 19 | 90 | YES | (Pair Porgrammed with Angie and Isabella)
US01 | Dates before current date | JJ | Done | 60 | 50 | 84 | 60 | YES | (Paired Programming with Justin, Angie, Dupuy)
US02 | Birth before marriage | JJ | Done | 60 | 60 | 63 | 30 | YES
US03 | Birth before death | AZ | Done | 60 | 40 | 39 | 15 | YES
US04 | Marriage before death | AZ | Done | 60 | 45 | 142 | 60 | YES
US05 | Marriage before divorce | OP | Done | 60 | 30 | 45 | 45 | YES
US06 | Divorce before death | OP | Done | 60 | 60 | 152 | 30 | YES | (Pair Programmed Olivia and Jenn)
US07 | Less then 150 years old | JL | Done | 60 | 60 | 35 | 35 | YES
US08 | Birth before death of mother | MD | Done | 60 | 57 | 46 | 30 | YES
US09 | Birth before marriage of parents | JL | Done | 60 | 60 | 42 | 20 | YES | (Pair Programmed Olivia and Jenn)
US10 | Marriage after 14 | MD | Done | 60 | 60 | 53 | 30 | YES | (Paired Programming with Justin and Dupuy)
Total |  |  |  | 660 | 582 | 720 | 445
Review Results
Good to pivot to python- made project a lot easier
Pair programming over visual code helped a lot
Keep doing:
| Pair programming made coding user stories a lot easier |  |  | ***ONLY EDIT BACKLOG for story name, owner, status
Meeting up after class wednesdays and sunday nights
Avoid:
Working on this assignement at the last minute
Not responding in the groupchat to messages
Missing group meetings
Losing more group members

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US11 | No bigamy | JL | Done | 30 | 40 | 120 | 180 | YES
US12 | No child born after divorce | JL | Done | 100 | 20 | 65 | 120 | YES
US13 | Conception before Fathers Death | JJ | Done | 150 | 30 | 62 | 35 | YES
US14 | Parents not too old | JJ | Done | 200 | 20 | 101 | 60 | YES
US15 | Siblings spacing | MD | Done | 100 | 40 | 78 | 60 | YES
US16 | Multiple births <= 5 | MD | Done | 200 | 30 | 112 | 60 | YES
US17 | Fewer than 15 siblings | OP | Done | 250 | 30 | 56 | 30 | YES
US18 | Male last names | OP | Done | 150 | 45 | 91 | 40 | YES
US19 | No marriages to descendants | AZ | Done | 125 | 60 | 51 | 45 | YES
US20 | Siblings should not marry | AZ | Done | 135 | 45 | 69 | 30 | YES
Total |  |  |  | 1410 | 320 | 685 | 480
***ONLY EDIT BACKLOG
***check Stories tab for description
Note:
Need to find long term solution to Dupuy VS branching problem
Isabella Wiley dropped out of the class, so we removed tasks that will not be done by the group.
Review Results
Keep Doing
Branching is really effective at controlling pushes to master
Pair Programming
Avoid:
Accidentally merging individual user stories from the master and not their own branch

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US21 | First cousins should not marry | JL | In Progress | 150 | 35
US22 | Aunts and uncles | JL | In Progress | 75 | 45
US23 | Correct gender for role | MD | In Progress | 45 | 75
US24 | Unique IDs | MD | In Progress | 150 | 35
US25 | Unique name and birth date | JJ | In Progress | 200 | 35
US26 | Unique families by spouses | JJ | In Progress | 100 | 40
US27 | Unique first names in families | AZ | In Progress | 200 | 45
US28 | Corresponding entries | AZ | In Progress | 75 | 45
US29 | Include individual ages | OP | In Progress | 150 | 45
US30 | Large age gaps between couples | OP | In Progress | 125 | 45
Total |  |  |  | 1000 | 290 | 0 | 0
***ONLY EDIT BACKLOG
***check Stories tab for description

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US31 | Order siblings by age | JL | TBD | 45 | 90
US32 | List deceased | JL | TBD | 150 | 75
US33 | List living married | MD | TBD | 200 | 80
US34 | List living single | MD | TBD | 100 | 95
US35 | List multiple births | AZ | TBD | 200 | 100
US36 | List recent births | JJ | TBD | 250 | 45
US37 | List recent deaths | JJ | TBD | 150 | 45
US38 | List upcoming birthdays | OP | TBD | 125 | 60
US39 | List upcoming anniversaries | OP | TBD | 135 | 45
US40 | Reject illegitimate dates | AZ | TBD | 150 | 35
Total |  |  |  | 1505 | 670 | 0 | 0
***ONLY EDIT BACKLOG
***check Stories tab for description

## Stories
Story ID | Story Name | Story Description
US00 | Creating datetime objects | Dates (birth, death, marriage, divorce) should be stored as datetime object properties of individuals and families for streamlined implementation of the other user stories
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage for both spouses
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before death | Marriage should occur before death of either spouse
US05 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before death of mother | Child should be born before death of mother
US09 | Birth before marriage of parents | Children should be born after marriage of parents
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | No child born after divorce | Children should be born no more than 9 months after their divorce
US13 | Conception before Fathers Death | Child should be born before 9 months after death of father
US14 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US15 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US16 | Multiple births <= 5 | No more than five siblings should be born at the same time
US17 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US18 | Male last names | All male members of a family should have the same last name
US19 | No marriages to descendants | Parents should not marry any of their children
US20 | Siblings should not marry | Siblings should not marry one another
US21 | First cousins should not marry | First cousins should not marry one another
US22 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US23 | Correct gender for role | Husband in family should be male and wife in family should be female
US24 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US25 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US26 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US27 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US28 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US29 | Include individual ages | Include person's current age when listing individuals
US30 | Large age gaps between couples | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US31 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US32 | List deceased | List all deceased individuals in a GEDCOM file
US33 | List living married | List all living married people in a GEDCOM file
US34 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US35 | List multiple births | List all multiple births in a GEDCOM file
US36 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US37 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)